REPUBLIC OF GHANA

FANTEAKWA NORTH DISTRICT ASSEMBLY

2025 COMPOSITE ANNUAL ACTION PLAN

PREPARED BY: DISTRICT PLANNING CO-ORDINATING UNIT

OCTOBER, 2024

Contents

DISTRICT MEDIUM- TERM DEVELOPMENT PLAN (2022-2025)	3

FANTEAKWA NORTH DISTRICT ASSEMBLY ANNUAL ACTION PLAN FOR THE YEAR 2025	3

IMPLEMENTATION ARRANGEMENT AND ANNUAL ACTION PLAN	3

Mobilization of Local Resources	4

Partnership with External Agencies.	4

Resource Utilization	4

Institutional linkages	4

Project Selection Consideration	5

Project Financing	5

Programme Budgeting System	5

List of table

Tab. 1. Fanteakwa North District Assembly 2025 Composite Annual Action Plan……………….7

# DISTRICT MEDIUM- TERM DEVELOPMENT PLAN (2022-2025)

## FANTEAKWA NORTH DISTRICT ASSEMBLY ANNUAL ACTION PLAN FOR THE YEAR 2025

### IMPLEMENTATION ARRANGEMENT AND ANNUAL ACTION PLAN

Specific interventions have been proposed under the (four) 4-Year Medium Term Development Plan (2022 –2025) Priority projects have also been proposed for the Socio-Economic Development of the District, and a summary of the interventions provided. Priority projects have been selected taking cognizance of the potentials and opportunities that abound in the District. This will enable the plan to enjoy support with available human and financial resources within the 4- Year Plan period (2022-2025).

Fanteakwa North District Assembly has assigned to itself the co-ordination and implementation role at the local level. The District Medium Term Development Plan indicates the responsibility or principal action agent, as well as collaborating agents and their roles including that of development partners; or relevant organizations are identified to implement the various aspects of the proposed interventions outlined in the plan. Financially it provides information on implementation schedule and crude estimates of projects.

The interlinkages of the causes and effects of the identified core problems in the major sectors of the District economy is to adopt an integrated and co-ordinated strategy. The best option, in the circumstance, therefore, will be to integrate the priority needs in the health sector with opportunities in agriculture, education and improvement in the economic infrastructure, especially roads to ensure maximum benefits.

It has also been realized that it may not be possible to adhere strictly to the implementation schedules proposed for the various sector plans as a result of scares resources. Indeed, the proposed implementation schedules are to serve as guidelines from which feasible combination of interventions can be put together in a specific year.

In the first year, efforts are to be concentrated on rehabilitation and construction of essential services in areas of water, sanitation an improvement in health services and education. This is in line with attending to the immediate priority and basic needs of the people which include water, sanitation education, health, job creation and strengthening of small and medium scale enterprises.

The effective implementation of the 4-Year District Medium Term Development Plan (DMTDP), calls for an approach that seeks to optimize utilization of available internal and external resources.

Consequently, the implementation strategy will be:

- Mobilization of local resources

- Partnership with external agencies

- Prudent use of available resources; and

- Cohesive institutional linkages and networking.

# Mobilization of Local Resources

An effective mobilization of local resources both human and material will go a long way to ensure smooth implementation of the plan. The active participation of the local communities in the planning and implementation of the 4-Year Medium Term Plan is very crucial.

Because effective planning and implementation of programmes and projects are interactive processes and it takes place among people and between institutions at different levels. Therefore, the successful implementation of the plan will depend on.

- Availability of funds

- Effectiveness of the plan in terms of degree of local involvement.

- Level of community involvement and the willingness to contribute labour, money and other local resources.

- And adequate local institutional support.

The Departments in the District must be encouraged to play active role in the implementation of their respective sectoral plans and available material resources. Co-ordination among the Departments must be ensured to bring about the advantage of sectoral integration for the implementation of the entire Development Plan.

## Partnership with External Agencies.

Even though, the District is independent in terms of planning and administrative decisions at the local level, limitation in human and financial resources make it imperative for the District to seek external support.

Analysis of the District Assembly’s finances is evident that it will be impossible for it to implement any meaningful projects from its own resources. Therefore, external resources from the Central Government, GETFUND, DACF-RFG must be vigorously sought for by the assembly as important complementary sources of funding to execute the plan.

Lastly, local groups, especially at the community levels must be animated to play active roles in the implementation of some aspect of the Development Plan e.g. capacity building for zonal Council Members to participate in Needs Assessment.

# Resource Utilization

With limited resource, financial, material and human, it is not possible to satisfy the needs of all communities within the 4-Year period.

On the basis of the above, projects should be sited strategically to serve many communities as much as possible. Secondly, projects selected should serve the felt needs of the communities and not political interest.

# Institutional linkages

As much as possible, institutional capacity building should be pursued. The District Assembly should assume the overall central co-coordinating role while outlining institutional responsibilities in conjunction with the various departments and other governance agencies. This is to get them actively involved in implementation on the plan in its totality.

Agencies outside must also be consulted to give assistant to the Assembly’s own implementation and monitoring efforts. Research institutions of the various Universities such as BIRD, BRRI, CSIR, etc could be of immense help in the areas of planning, training and advise on project implementation, monitoring and evaluation.

In order to achieve some level of integration, planning and project implementation have to be work out in such a way that the development of one sector is in linked to the other sectors of the economy of the District.

This way the development of feeder roads is meant to positively affect agriculture production. Much the same, the provision of portable water is expected to supplement health delivery in the District.

# Project Selection Consideration

Pragmatic approach guided in the selection and location of projects. This was to avoid pressure from communities and authorities. The process involved open for communal participation in the needs assessment procedure. Care was also taken to ensure equitable distribution of projects to ensure that:

- Selected projects respond to the priority needs of the community.

- Project selected are accessible to the majority of the people in the community.

- Technology choice for implementation is user friendly.

- Resources for implementation is available

- That the project will be sustainable (e.g.) a school must have encouraging enrolment rate.

- The project is aimed at poverty reduction in the District.

# Project Financing

The implementation of projects and programmes under the 4-year Medium Term plan will require huge financial resources. Obviously, such financial resources cannot be generated within the District alone over the planned period. Even with its share of the Common Fund, the District will still need extra funding from central government and other agencies.

The main sources therefore should include:

- The District Assembly sources (IGF)

- Central Government

- GETFUND

- MPs Common Fund

- LEAP

- United Nations Capital Development Fund (UNCDF)

- DACF-RFG

- DACF

# Programme Budgeting System

In order to successfully implement programmes and projects as spelt out in the plan. A programme budgeting system must be put in place. This allows for allotment of adequate funding to different areas of the programme. This entails a clear description of the projects involved and matching of specific projects or programme budgeting is that is link to specific prioritize projects. Therefore, in reduction in allocation from the planned budget can be easily identified with a particular project, which easily leads to corresponding exclusion of specific projects rather than to squeezing all programmes inefficiently.

It must be noted that the effective and successful implementation of programmes of the Fanteakwa North District 4-year Medium Term Plan will depend heavily on the authority and capacity of the Assembly, and the participation and integration of all the people in all stages of the development process, namely, project planning, implementation, monitoring and evaluation.

The tables that follow show the Annual Action Plan for Fanteakwa North District Assembly indicating specific project intervention for the year 2025 as planned.

| FANTEAKWA NORTH DISTRICT ASSEMBLY 2025 COMPOSITE ANNUAL ACTION PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEVELOPMENT DIMENSION: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADOPTED GOAL:Creat Opportunities For All Ghanaians |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME | SUB-PROGRAMME | NO | ACTIVITY/PROJECT/OPERATION | LOCATION | SDG TARGETS | BASELINE | OUTPUT INDICATOR | QUARTERLY TIME SCHEDULE |  |  |  | FUNDING SOURCE |  |  |  |  |  |  | PROGRAMME STATUS |  |  | IMPLEMENTING AGENCIES |  |
|  |  |  |  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | DACF | DP | GoG | DACF-RFG | MP's FUND | IGF | NEW |  | ONGOING | LEAD |  | COLLABORATOR |
| Social Service Delivery | Education, Youth & Sports | 1 | Support District Level Independence Day Celebration | Begoro |  |  | Independence Day celebration supported | X |  |  |  |  |  |  |  |  | 30,000.00 | X |  |  | GES |  | FNDA |
|  |  | 2 | Conduct SPAM in schools | District-wide |  |  | Number of schools involved |  |  |  | X |  |  | 12,000.00 |  |  |  |  |  | X | GES |  | FNDA |
|  |  | 3 | Support brilliant but needy students | District-wide |  |  | Count of students supported | X |  |  | X | 10,000.00 |  |  |  |  |  |  |  | X | GES |  | FNDA |
|  |  | 4 | Completion of 1No.6-unit primary classroom block with 6-seater KVIP toilet | Meyiwa-Krobo |  |  | Number of classrooms& KVIP seaters completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GES |
|  |  | 5 | Completion of 1No.teachers’ quarters with mechanised borehole | Meyiwa-Bosanko |  |  | Number of rooms & boreholes completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GES |
|  |  | 6 | Completion of 1No.3-unit KG block with office, store, library, staff common room,1No.4-seater toilet & 1No.2-cuble urinal | Begoro Zion |  |  | Number of units, office, store, library, common room and urinal cubicles completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GES |
|  | Health Delivery | 7 | Campaign against HIV/AIDS, Malaria & TB | District-wide |  |  | Amount of funds involved | X | X | X | X |  |  | 2,000.00 |  |  |  | X |  |  | GHS |  | FNDA |
|  |  | 8 | Addressing high prevalence rate of HIV in the district | District-wide |  |  | Amount of funds involved | X | X | X | X |  |  | 1,500.00 |  |  | 1,500.00 | X |  |  | GHS |  | FNDA |
|  |  | 9 | Prevention of maternal deaths and the improvement of maternal health services | District-wide |  |  | Number of maternal deaths prevented | X | X | X | X |  |  | 5,000.00 |  |  |  | X |  |  | GHS |  | FNDA |
|  |  | 10 | Enhancing malaria control, especially among pregnant women and children | District-wide |  |  | Number of malaria cases reported among pregnant women and children | X | X | X | X |  |  |  |  |  | 2000 | X |  |  | GHS |  | FNDA |
|  |  | 11 | Incorporating networks of practices in the district | District-wide |  |  | Number of Network of practices incorporated | X | X | X | X |  |  | 3,000.00 |  |  |  | X |  |  | GHS |  | FNDA |
|  |  | 12 | Completion of 1No. Maternity block with mechanised borehole | Ahomahomasu |  |  | Number of rooms & mechanised boreholes completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GHS |
|  |  | 13 | Completion of 1No.maternity home with mechanised borehole | Abourso |  |  | Number of rooms & mechanised boreholes completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GHS |
|  |  | 14 | Completion of 1No.nurses' quarters with mechanised borehole | Adakope |  |  | Number of rooms & mechanised borehole completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | GHS |
|  |  | 15 | Construction of 1No.CHPs compound with 1No.mechanised borehole | Anyinasin |  |  | Number of rooms & mechanised boreholes completed | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | GHS |
|  |  | 16 | Medical screening of 1,500 No. food and drink handlers | District-wide |  |  | Number of food and drink handlers screened | X | X | X | X |  |  |  |  |  | 97,500.00 |  |  | X | DEHU |  | FNDA |
|  | Social Welfare & Community Development | 17 | Registration and Data Update of 50 No. Vulnerable Groups (Children, Aged and PWDs) in 10 No. communities | District-wide |  |  | Number of vulnerable groups registered | X | X | X | X | 1,000.00 |  | 1000.00 |  |  | 1,000.00 | X |  |  | DSWCD |  | FNDA |
|  |  | 18 | Support 50 No. of Persons with Disability with various items and financial support for health and education and Training of 30 No. of PWDs on alternative livelihood | District-wide |  |  | Number of PWDs supported and trained | X | X | X | X | 1,000.00 |  | 2000 |  |  | 1,000.00 | X |  |  | DSWCD |  | FNDA |
|  |  | 19 | Payment of LEAP in 36No. communities | District-wide |  |  | Number of LEAP beneficiaries paid | X | X | X | X |  |  | 611,568.00 |  |  |  | X |  |  | DSWCD |  | FNDA |
|  |  | 20 | Community sensitization in 10 No. communities on Child rights, child labour, child abuse, teenage pregnancy and monitor 5 child abuse cases in the above indicated number of communities. | District-wide |  |  | Number of communities sensitised | X | X | X | X | 1,000.00 |  | 2000.00 |  |  | 1,000.00 | X |  |  | DSWCD |  | FNDA |
|  |  | 21 | Register and Monitor 10 No. of Day Care Centres in 5 No. communities | District-wide |  |  | Number of daycare centres monitored and registered | X | X | X | X | 100.00 |  | 500.00 |  |  | 100.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 22 | Settle and monitor 30 child welfare cases. | District-wide |  |  | Number of cases settled | X | X | X | X | 1,000.00 |  | 1000.00 |  |  | 1,000.00 | X |  |  | DSWCD |  | FNDA |
|  |  | 23 | Conduct Home Visits on 15 child welfare Cases in 15 No. communities | 10 communities |  |  | Number of communities sensitised | X | X | X | X | 1,000.00 |  | 2000.00 |  |  | 1,000.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 24 | Sensitize 10 No. communities on Gender Based issues | District-wide |  |  | Number of communities sensitised | X | X | X | X | 200.00 |  |  | 1000.00 |  | 300.00 | X |  |  | DSWCD |  | FNDA |
|  |  | 25 | Extension Services (Collaboration with other Departments/units) | District-wide |  |  |  | X | X | X | X | 1,000.00 |  | 1000.00 |  |  | 1,000.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 26 | Offer Psycho-Social Counselling to 10 No. HIV/AIDS Patients and medico-social support to 10 No. paupers to pay their hospital bills | District-wide |  |  | Number of persons counselled & supported | X | X | X | X | 5,000.00 |  | 5000.00 |  |  | 5,000.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 27 | Make representation at the Juvenile court and Family Tribunal in 10 No. of communities | 10 communities |  |  | Report on cases settled | X | X | X | X |  |  |  |  |  |  | X |  |  | DSWCD |  | FNDA |
|  |  | 28 | Register and renew NHIS cards for 20 No. PWDs & 50No. LEAP beneficiaries | District-wide |  |  | Number of PWDs & LEAP beneficiaries renewed on NHIS card | X | X | X | X |  |  |  |  |  | 1,000.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 29 | Monitor Rehabilitation Centre | Begoro |  |  | Number of rehabilitation centres monitored | X | X | X | X | 1,000.00 |  |  |  |  | 1,000.00 |  |  | X | DSWCD |  | FNDA |
|  |  | 30 | Register and monitor 3 NGOs in the District Partner 3 NGOs in executing NGO/Social Welfare activities in 15No. Communities | 15 communities |  |  | Number of NGOs registered & monitored | X | X | X | X | 200.00 |  | 200.00 |  |  | 100.00 |  |  |  | DSWCD |  | FNDA |
|  |  | 31 | Sensitization and engagement on teenage pregnancy | 5no. Communities |  |  | Number of communities engaged | X | X | X | X | 5,000.00 |  |  |  |  |  |  |  | X | DSWCD |  | FNDA |
|  |  | 32 | Sensitization on drug abuse among children | 5no. Communities |  |  | Number of children sensitized | X | X | X | X | 18,420.00 |  |  |  |  |  | X |  |  | GENDER |  | FNDA |
|  |  | 33 | Community durbars on child labour / abuse | 5no. Communities |  |  | Number of durbars held |  | X |  | X | 6,500.00 |  |  |  |  | 2,710.00 | X |  |  | GENDER |  | FNDA |
|  |  | 34 | Training of female participation in decision making process | 5no. Communities |  |  | Number of females trained | X | X | X | X | 6,500.00 |  |  |  |  | 2,710.00 | X |  |  | GENDER |  | FNDA |
|  |  | 35 | Sensitization on high school drop out | 5no. Communities |  |  | Number of communities sensitized | X | X | X | X | 10,000.00 |  |  |  |  | 8,420.00 | X |  |  | GENDER |  | FNDA |
|  |  | 36 | Community/school sensitization on low girl child enrolment in schools | 5no. Communities |  |  | Number of communities sensitized | X | X | X | X | 10,000.00 |  |  |  |  | 8,420.00 | X |  |  | GENDER |  | FNDA |
| DEVELOPMENT DIMENSION: Environment,Infrastructure and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADOPTED GOAL:Saveguard The Natural Environment & Ensure A Resilient, Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery & Management | Physical & Spatial Planning | 37 | Preparation of planning schemes | District-wide |  |  | Number of planning schemes prepared | X | X | X | X | 90,000.00 |  |  |  |  |  |  |  | X | PPD |  | FNDA |
|  |  | 38 | Public education on permitting and local plan | District-wide |  |  | Number of public educations carried out | X | X | X | X |  |  |  |  |  | 10,000.00 |  |  | X | PPD |  | FNDA |
|  |  | 39 | Registration of Assembly land banks | District-wide |  |  | Size of assembly lands registered | X | X | X | X |  |  |  |  |  | 40,000.00 |  |  | X | PPD |  | FNDA |
|  |  | 40 | Street naming and property addressing | District-wide |  |  | Number of properties and streets numbered and named | X | X | X | X | 100,000.00 |  |  |  |  |  |  |  | X | PPD |  | FNDA |
|  |  | 41 | Monitoring of development structures | District-wide |  |  | Number of structures monitored | X | X | X | X |  |  | 15,000.00 |  |  |  |  |  | X | PPD |  | FNDA |
|  |  | 42 | Nursering of seedlings | Begoro |  |  | Number of seedlings nursed | X | X | X | X | 10,000.00 |  |  |  |  |  |  |  | X | PPD |  | FNDA |
|  | Infrastructure development | 43 | Rehabilitation of General Assembly Hall | Begoro |  |  | General Assembly Hall rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 44 | Rehabilitation of Ahomahomasu-Adentem-tweapease feeder roads(4km) | Ahomahomaso-Tweapease |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 45 | Rehabilitation of Dedeso-Napanya feeder roads & others(6km) | Dedeso-Napanya |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 46 | Rehabilitation of Deduako-Amiawa-Hyehoden-Addokrom feeder roads(3km) | Deduako-Addokrom |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 47 | Rehabilitation of Agric office-Zongo road(0.8km) | Begoro |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 48 | Rehabilitation of Salvation jnc-Bethlehem(0.6km) | Begoro |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 49 | Rehabilitation of Abiola jnc-Fire Service Road(2.5km) | Begoro |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 50 | Rehabilitation of Otuater-ofosukrom and others(4.5km) | Otuater-Ofosukrom |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 51 | Rehabilitation of Nyadie-Aburaso-Aboabo feeder roads(4km) | Nyadie-Aboabo |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 52 | Rehabilitation of Bisibuom jnc-Bisibuom feeder roads(4.5km) | Bisibuom jnc-Bisibuom |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 53 | Rehabilitation of Asarekwao-Kyerepon feeder roads(2km) | Asarekwao-Kyerepon |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 54 | Rehabilitation of Asirebuso-Miaso feeder roads(1.5km) | Asirebuso-Miaso |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 55 | Rehabilitation of Onuku-Akoadarko feeder roads | Onuku-Akoadarko |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 56 | Desilting of chocked gutter | Oposoroowor |  |  | Length of gutter desilted | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 57 | Rehabilitation of Oposoroowo-Odumase Jnc | Oposoroowor-Odumase |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 58 | Drilling and construction of 2No. Boreholes | Akumersu-East & Sukuma |  |  | Number of boreholes drilled and constructed | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 59 | Rehabilitation of Otuater-Abourso feeder rods | Otuater-Abourso |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 60 | Rehabilitation of Ahomahomasu-Amotare feeder roads | Ahomahomasu-Amotare |  |  | Length of km rehabilitated | X | X | X | X |  |  |  |  |  |  | X |  |  | DWD |  | FNDA |
|  |  | 61 | Completion of 1No.community mechanised borehole | Dominase |  |  | Number of boreholes completed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 62 | Provision for LoCAL Funded projects | District-wide |  |  | Number of projects | X | X | X | X |  | 500,000.00 |  |  |  |  |  |  | X | FNDA |  | LoCAL |
| Environmental & Sanitation Management |  | 63 | Clean-up exercise | 6No. Communities |  |  | Number of communities benefited | X | X | X | X | 16,000.00 |  |  |  |  |  |  |  | X | DEHU |  | NADMO, Forestry |
|  |  | 64 | Community Led Total Sanitation (CLTS) | 6No. Communities |  |  | Number of communities sensitised | X | X | X | X |  |  |  |  |  | 12,000.00 |  |  | X | DEHU |  | FNDA |
|  |  | 65 | Data collection on household and institutions with water and sanitation facilities (WASH) | District-wide |  |  | Number of households,bars and institutions recorded | X | X | X | X |  |  |  |  |  | 28,000.00 | X |  |  | DEHU |  | FNDA |
|  |  | 66 | Arrest of stray animals | District-wide |  |  | Number of stray animals arrested | X | X | X | X |  |  |  |  |  | 3,000.00 |  |  | X | DEHU |  | FNDA |
|  |  | 67 | Levelling of final disposal site | District-wide |  |  | Final disposal site levelled | X | X | X | X | 10,000.00 |  |  |  |  | 5,000.00 |  |  | X | DEHU |  | FNDA |
|  |  | 68 | Fumigation and disinfection | 5no. Communities |  |  | Number of communities fumigated & disinfected | X | X | X | X | 53,187.50 |  |  |  |  |  |  |  | X | DEHU |  | FNDA |
|  |  | 69 | Stores and domiciliary inspection | District-wide |  |  | Number of stores inspected | X | X | X | X |  |  |  |  |  | 44,000.00 |  |  | X | DEHU |  | FNDA |
|  |  | 70 | Sanitation improvement package (SIP) | District-wide |  |  | Number of items of sanitation improvement package provided | X | X | X | X |  |  |  |  |  | 31,000.00 | X |  |  | DEHU |  | FNDA |
|  |  | 71 | Management and control of cemetery | District-wide |  |  | Number of cemeteries controled and managed | X | X | X | X |  |  |  |  |  | 7,000.00 |  |  | X | DEHU |  | FNDA |
|  |  | 72 | Sustainable WASH financing Project (Counterpart funding) | 3 no. communities |  |  | Number of communities benefited | X | X | X | X |  |  |  |  |  |  | X |  |  | FNDA |  | World Vision, Vision Fund |
| DEVELOPMENT DIMENSION: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADOPTED GOAL: Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disaster prevention & management |  | 73 | Bushfire Education | All zones |  |  | Number of zones educated | X | X | X | X |  |  | 10,000.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 74 | Inspection of Firefighting Equipment | Begoro |  |  | Number of homes/institutions inspected | X | X | X | X |  |  | 5,500.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 75 | Organize 4No. DDMC Meeting | Begoro |  |  | Number of DDMC meetings held | X | X | X | X |  |  | 2,700.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 76 | Education on Disaster Risk Reduction | All zones |  |  | Number of zones educated | X | X | X | X |  |  | 8,000.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 77 | International Day for Disaster Risk Reduction (IDDRR, 2025) | Begoro |  |  | Report on celebration of IDDRR 2025 | X | X | X | X |  |  | 5,900.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 78 | Hazard identification | Begoro |  |  | Number of hazards identified | X | X | X | X |  |  | 3,400.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 79 | Awareness creation on spillage of Bagre dam | 16No. Communities |  |  | Number of communities sensitised | X | X | X | X |  |  | 4,600.00 |  |  |  |  |  | X | NADMO |  | FNDA |
|  |  | 80 | Tree Planting Exercise | District-wide |  |  | Number of seedlings planted | X | X | X | X |  |  | 4,200.00 |  |  |  |  |  | X | Forestry |  | NADMO, PPD, AGRIC, GES |
|  |  | 81 | Support for fight against COVID-19 | District-wide |  |  | Amount of funds involved | X | X | X | X |  |  | 3,000.00 |  |  | 2,000.00 | X |  |  | GHS |  | FNDA |
| DEVELOPMENT DIMENSION: Governance, Corruption and Public Accountability. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management & Administration | Research,statistics & information management | 82 | Administrative data compilation(update) | District-wide |  |  | Reports on data collection | X | X | X | X |  |  |  |  |  | 3,000.00 |  |  | X | Statistics |  | FNDA |
|  |  | 83 | Creation of business register | Begoro |  |  | Number of businesses recorded |  | X | X |  | 7,000.00 |  |  |  |  | 5,000.00 | X |  |  | Statistics |  | FNDA |
|  |  | 84 | Collect data on Assembly properties | District-wide |  |  | Number of Assembly properties recorded | X | X | X | X |  |  | 4,000.00 |  |  |  |  |  | X | Statistics |  | Works |
|  |  | 85 | Purchase of Office Logistics: • Desktop – 1 • Laptop – 1 • Printer – 1 • Swivel Chair – 1 | Begoro |  |  | Number of Desktop, laptop, printer, swivel chair purchased | X | X | X | X | 10,000.00 |  |  |  |  |  | X |  |  | HR |  | FNDA |
|  |  | 86 | Purchase of Office Logistics: •Ceiling fan – 1 •Air Conditioner – 1 •Sofa – 1 | Begoro |  |  | Number of Ceiling fan, Air conditioner, sofa purchased | X | X | X | X | 10,000.00 |  |  |  |  |  | X |  |  | CSU |  | FNDA |
|  |  | 87 | Website and Social Media Management | Begoro |  |  | Number of Website and Social managed | X | X | X | X |  |  |  |  |  | 1,000.00 |  |  | X | MIS |  | FNDA |
|  |  | 88 | Software and Hardware Maintenance | Begoro |  |  | Number of Software and Hardware maintained | X | X | X | X |  |  |  |  |  | 1,000.00 |  |  | X | MIS |  | FNDA |
|  |  | 89 | IT Technical Support and Training | Begoro |  |  | Number of support and training given | X | X | X | X |  |  |  |  |  | 5,000.00 |  |  | X | MIS |  | FNDA |
|  |  | 90 | Procure Office Stationery and Equipment | Begoro |  |  | Number of Office Stationery and Equipment procured | X |  |  |  | 80,000.00 |  |  |  |  |  |  |  | X | Procurement |  | FNDA |
|  | Legislative oversight | 91 | Establish 30No. complaints boxes at vantage points within the district and toll-free hotline | All zonal councils |  |  | Number of Complaint boxes, toll-free hotlines established |  | X | X | X | 7,000.00 |  |  |  |  | 5,000.00 |  |  | X | FNDA |  |  |
|  |  | 92 | Organise 6No. Public Education on the availability and usage of client service toll-free lines | All zonal councils |  |  | Number of public educations carried out | X | X | X | X |  |  |  |  |  | 2,000.00 | X |  |  | FNDA |  | NCCE |
|  |  | 93 | Organise 6No.public durbar on Whistleblowers Act 720 2006 | All zonal councils |  |  | Number of durbars held | X | X | X | X | 5,00.00 |  |  |  |  | 4,000.00 | X |  |  | FNDA |  | NCCE/CHRAJ |
|  |  | 94 | Print and distribute 2000No. anti-corruption fliers and brochures | District-wide |  |  | Number of fliers and brochures distributed | X | X | X | X |  | 15,000.00 |  |  |  | 5,000.00 |  |  |  | FNDA |  | NCCE/CHRAJ |
|  |  | 95 | Undertake Compliance Audit | Begoro |  |  | Number of Audit reports | X | X | X | X |  |  |  |  |  |  | X |  |  | IAU |  | FNDA |
|  |  | 96 | Undertake Performance Audit | Begoro |  |  | Number of Audit reports | X | X | X | X |  |  |  |  |  |  | X |  |  | IAU |  | FNDA |
|  |  | 97 | Undertake Quality Assurance Audit | Begoro |  |  | Number of Audit reports | X | X | X | X |  |  |  |  |  |  | X |  |  | IAU |  | FNDA |
|  |  | 98 | Undertake Financial Audit | Begoro |  |  | Number of Audit reports | X | X | X | X |  |  |  |  |  |  | X |  |  | IAU |  | FNDA |
|  |  | 99 | Undertake Information Technology Audit | Begoro |  |  | Number of Audit reports | X | X | X | X |  |  |  |  |  |  | X |  |  | IAU |  | FNDA |
|  |  | 100 | Conduct 4no. Management meetings | Begoro |  |  | Number of management meetings held | X | X | X | X | 10,000.00 |  |  |  |  | 5,000.00 | X |  |  | FNDA |  |  |
|  |  | 101 | Conduct 3no. General Assembly meetings | Begoro |  |  | Number of GA meeting held | X | X | X | X | 15,000.00 |  |  |  |  | 5,000.00 | X |  |  | FNDA |  |  |
|  |  | 102 | Conduct 4no. Executive committee meetings | Begoro |  |  | Number of executive committee meetings held | X | X | X | X | 12,000.00 |  |  |  |  | 5,000.00 |  |  | X | FNDA |  |  |
|  |  | 103 | Organise statutory subcommittee meetings | Begoro |  |  | Number of statutory meetings held | X | X | X | X | 10,000.00 |  |  |  |  | 6,000.00 |  |  | X | FNDA |  |  |
|  |  | 104 | Organise 18No. Meetings for the Six (6) urban/town/area councils | All zonal councils |  |  | Number of Meetings organised | X | X | X | X | 20,000.00 |  |  |  |  | 7,000.00 | X |  |  | FNDA |  | Central Admin |
|  |  | 105 | Public sensitisation & awareness on the early registration of birth and death within the communities | District-wide |  |  | Reports on sensitisation | X | X | X | X |  |  |  |  |  | 4,200.00 |  |  | X | B&D |  | FNDA |
|  |  | 106 | Pay regular visit to hospital facilities & CHPs compound to register infants under a year old in selected communities | Begoro, Obooho, Akoradako, Ahomahomaso, Amokrom, Asarekwao |  |  | Number of health facilities visited | X | X | X | X | 2,000.00 |  |  |  |  | 4,000.00 |  |  | X | B&D |  | FNDA |
|  |  | 107 | Organise outreach registration exercises (mobile registration for hinter communities | District-wide |  |  | Number of communities reached | X | X | X | X | 2,000.00 |  |  |  |  |  |  |  | X | B&D |  | FNDA |
|  |  | 108 | Establish reporting centres & monitoring of their activities | District-wide |  |  | Number of centres established | X | X | X | X |  |  |  |  |  | 3,000.00 |  |  | X | B&D |  | FNDA |
|  |  | 109 | Provide Technical and Administrative Service to the District | Begoro |  |  |  | X | X | X | X |  |  |  |  |  | 1,000.00 |  |  | X | B&D |  | FNDA |
|  |  | 110 | LGS Performance Contract Activities: a) PC Mid-year Review meeting b) PC End-of-Year meeting c) Review of 2024 PC Performance in 2025 | Assembly Hall, Begoro |  |  | Number of participants | X |  | X | X |  |  |  |  |  | 10,000.00 | X |  | X | HR |  | FNDA |
|  | Planning budget & co-ordination | 111 | DCE engagement with communities | District-wide |  |  | Number of communities engaged | X | X | X | X |  |  |  |  |  | 5,000.00 |  |  | X | FNDA |  | Communities |
|  |  | 112 | Servicing of (6) official Assembly vehicles | District-wide |  |  | Number of vehicles serviced | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |
|  |  | 113 | Organise 2No.collaborative meetings between the Assembly, GWC, ECG and other essential service providers | Begoro |  |  | Number of collaborative meetings | X |  | X |  |  |  |  |  |  | 3,000.00 |  |  | X | FNDA |  | Utility providers |
|  |  | 114 | Support community-initiated projects | District-wide |  |  | Number of community-initiated projects supported. | X | X | X | X |  |  |  |  |  |  | X |  |  | FNDA |  |  |
|  |  | 115 | Organise 4No.entity tender committee meeting | Begoro |  |  | Number of entity committee meetings organised | X | X | X | X |  |  |  |  |  |  |  |  | X | FNDA |  |  |
|  |  | 116 | Preparation of 2026 TNA & CB Plan, Promotion Register & Leave Schedule | Begoro |  |  | Number of participants | X | X | X | X |  |  |  |  |  | 500.00 | X |  |  | HR |  | FNDA |
|  | Human resource development & management | 117 | Capacity building of staff and FBO's | Begoro |  |  | Number of participants |  | X |  |  |  |  | 1000.00 |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 118 | Training of Beneficiaries in Youth In Sanitation Module | Begoro |  |  | Number of beneficiaries trained | X | X | X | X |  |  |  |  |  |  |  |  | X | YEA |  |  |
|  |  | 119 | Capacity Building for Staff and Post-Training Impact Assessment on a) Local Governance Act 2016 (Act 936) b) Labour Law c) Assembly By-Laws d) Performance Contract & Performance Appraisal | Salvation Army Church Auditorium, Begoro |  |  | Number of staff trained | X | X | X | X | 30,000.00 |  |  |  |  |  |  |  | X | HR |  | FNDA |
|  |  | 120 | Orientation for Newly Recruited Staff and NSS Personnel | Assembly Hall, Begoro |  |  | Number Involved | X | X | X | X |  |  |  |  |  | 5.000.00 |  |  | X | HR |  | FNDA |
|  |  | 121 | Staff Durbar | Assembly Hall, Begoro |  |  | Number Involved | X | X | X | X | 70,000.00 |  |  |  |  |  |  |  | X | HR |  | FNDA |
|  |  | 122 | Organization of workshop for all staff of the Assembly on the new Records Management System | Begoro |  |  | Number of participants | X |  |  | X |  |  |  |  |  | 500 | X |  |  | Records |  | FNDA |
|  | Finance & revenue mobilisation | 123 | Implementation of RIAP (18) activities | Begoro |  |  | Number of activities implemented | X | X | X | X |  |  |  |  |  | 3,000.00 |  |  | X | FD |  | FNDA |
| DEVELOPMENT DIMENSION: IMPLEMENTATION, CORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADOPTED GOAL: Improve Delivery of Development Outcomes at all Levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Planning, budget, co-ordination, monitoring & evaluation | 124 | Organise 4No. DPCU meeting | Begoro |  |  | Number of reports/minutes | X | X | X | X |  |  |  |  |  | 12,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 125 | Undertake 4No. Montoring & Evaluation activities. | District-wide |  |  | Number of projects monitored | X | X | X | X | 20,000.00 |  |  |  |  | 5,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 126 | Organise Budget Committee meetings | Begoro |  |  | Number of meetings organised | X | X | X | X |  |  |  |  |  | 2,500.00 |  |  | X | FNDA |  |  |
|  |  | 127 | Organise 2024 Annual Review meeting | Begoro |  |  | Number of participants | X |  |  |  |  |  |  |  |  | 3,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 128 | Preparation of 2026-2029 DMTDP | Begoro |  |  | Amount of funds involved | X | X | X | X | 25,000.00 |  |  |  |  | 5,000.00 | X |  |  | DPCU |  | FNDA |
|  |  | 129 | Organise 2025 Mid-Year Review meeting | Begoro |  |  | Number of participants |  |  | X |  |  |  |  |  |  | 5,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 130 | Preparation of 2026 Composite Annual Action Plan | Begoro |  |  | Number of participants |  |  | X |  |  |  |  |  |  | 3,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 131 | Preparation of 2026 Composite Budget | Begoro |  |  | Number of participants |  |  | X |  |  |  |  |  |  | 3,000.00 |  |  | X | DPCU |  | FNDA |
|  |  | 132 | Town Hall meeting | Begoro |  |  | Number of town hall meetings organised | X |  | X |  | 17,000.00 |  |  |  |  | 4,000.00 |  |  | X | FNDA |  |  |
| DEVELOPMENT DIMENSION: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADOPTED GOAL:Build A Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agriculture Development | 133 | Home and Farm Visit to (4600) farmers | District-wide |  |  | Number of home and farm visited | X | X | X | X | 10,000.00 |  | 5,000.00 |  |  | 5,000.00 |  |  | X | DAD |  | FNDA |
|  |  | 134 | Monitoring visits on all activities | District-wide |  |  | Number of activities monitored | X | X | X | X |  |  |  |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 135 | Women Economic Empowerment and Entrepreneurship | District-wide |  |  | Number of women empowered |  | X |  |  |  |  | 1,000.00 |  |  | 1,000.00 | X |  |  | DAD |  | FNDA |
|  |  | 136 | Yield studies on production capacity | District-wide |  |  | Report produced | X | X | X | X |  |  |  |  |  | 3,000.00 | X |  |  | DAD |  | FNDA |
|  |  | 137 | Gender and disability inclusion programs (Alternative Livelihood Empowerment) | District-wide |  |  | Number of Gender and disability inclusion programmes undertaken | X | X | X | X | 5,000.00 |  |  |  |  | 5,000.00 | X |  |  | DAD |  | FNDA |
|  |  | 138 | Stakeholder Engagement along the Agric value chain (RELC and APPRS) | District-wide |  |  | Number of stakeholders engaged |  | X |  | X |  |  |  |  |  | 6,600.00 |  |  | X | DAD |  | FNDA |
|  |  | 139 | Farmers Day Celebration | District-wide |  |  | Reports on farmers day celebration |  |  |  | X | 300,000.00 |  |  |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 140 | Distribution Oil palm/Coconut seedlings (PERD) | District-wide |  |  | Number of seedlings distributed |  | X |  |  | 900.00 |  |  |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 141 | PFJ - Planting for food and Jobs | Begoro |  |  | Number of PFJ activities undertaken |  | X |  |  | 500.00 |  |  |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 142 | Rearing for food and jobs | District-wide |  |  | Number of RFJ activities undertaken | X |  |  |  | 500.00 |  |  |  |  |  | X |  |  | DAD |  | FNDA |
|  |  | 143 | Promotion of value-added products in the District | District-wide |  |  | Number of promotion activities organised |  | X |  |  |  |  |  |  |  | 4,000.00 |  |  | X | DAD |  | FNDA |
|  |  | 144 | Training in Climate Smart practices and establishing of demonstration farms | District-wide |  |  | Number of participants & demonstration farms established |  | X |  |  |  |  |  |  |  | 1,000.00 |  |  | X | DAD |  | FNDA |
|  |  | 145 | Organise financial literacy training for 50No. Youth | Begoro |  |  | Number of participants trained | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 146 | Organise Business Management training for 2No. Youth groups or Associations | Begoro |  |  | Number of participants trained | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 147 | Organise 3No. Entrepreneurship workshops for 3No. Women groups or youth groups | Begoro |  |  | Number of participants | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 148 | Organise scheduled individual meetings with 50No existing businesses for coaching and mentoring sessions | Begoro |  |  | Number of businesses coached or mentored | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 149 | Organise alternative livelihood training in soap and detergent making for 2No. Youth groups or Associations | Begoro |  |  | Number of participants trained | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 150 | Provision of Start-up kits to support apprentices engaged in various apprenticeship training under the GEA/Mastercard Foundation Business in a Box (BIZBOX) Project | Begoro |  |  | Number of apprentices supported | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 151 | Register selected 50No. enterprises with the BAC and helping them formalize their businesses with the RGD | Begoro |  |  | Number of enterprises registered with RGD | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 152 | Organise Internship or excursions for selected trade group members | Begoro |  |  | Number participants involved | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 153 | Engage stakeholders in the Association of Small Scale Industries (ASSI) in the district | Begoro |  |  | Number stakeholders engaged | X | X | X | X |  |  |  |  |  |  | X |  |  | BAC |  | FNDA |
|  |  | 154 | Local Economic Development (Women’s Group Empowerment in Skill Development in 10No. Communities) | 10 communities |  |  | Number of women groups empowered | X | X | X | X |  |  |  |  |  |  |  |  | X | DSWCD |  | FNDA |
|  |  | 155 | Completion of 1No.cassava processing shed with office, store and 1No.solar-powered mechanised borehole with overhead tank | Nteso No.1 |  |  | Number of shed, offices and borehole constructed | X | X | X | X |  |  |  |  |  |  |  |  | X | FNDA |  | BAC |
|  |  | 156 | Procurement & installation of cassava processing equipment | Nteso No1 |  |  | Number of equipment procured | X | X | X | X |  |  |  |  |  |  |  |  | X | FNDA |  | UNCDF |
|  |  | 157 | Completion of 1No.passenger lounge, revenue check point, 1No.2-seater toilet facility & 1cubicle urinal | Ahomahomaso |  |  | Number of lounge, revenue check point, toilet seater & urinal cubicle constructed | X | X | X | X |  |  |  |  |  |  |  |  | X | DWD |  | FNDA |